## Blank Action List
Name of project | [5 empty] | Date
No. | Action/Suggestion/ Recommendation | Person Responsible | Date/Time Due | % Not Complete | % Complete | Resolution/Status
1 |  |  |  | 100%
2 |  |  |  | 100%
3 |  |  |  | 100%
4 |  |  |  | 100%
5 |  |  |  | 100%
6 |  |  |  | 100%
7 |  |  |  | 100%
8 |  |  |  | 100%
9 |  |  |  | 100%
Name of project | [5 empty] | Date
No. | Action/Suggestion/ Recommendation | Person Responsible | Date/Time Due | % Not Complete | % Complete | Resolution/Status
10 |  |  |  | 100%
13 |  |  |  | 100%
14 |  |  |  | 100%
15 |  |  |  | 100%
16 |  |  |  | 100%
17 |  |  |  | 100%
18 |  |  |  | 100%

## Example Action List
QI Breastfeeding Promotion and Support Project | [5 empty] | 2009-09-03
No. | Action/Suggestion/ Recommendation | Person Responsible | Date/Time Due | % Not Complete | % Complete | Resolution/Status
1 | Survey providers for their feedback on Breast is Best & breastfeeding promotion and support | Sarah | 2009-09-30 | 10% | 90% | Survey designed and completed; Need to discuss the use of this feedback with Lynn & Sue
2 | Survey clients who breastfed on their successful breastfeeding and what they would like to see in WIC | Sarah | 2009-09-30 | 50% | 50% | Survey designed and completed; Needs additional implementation; Need to discuss the use of the feedback with Lynn & Sue
3 | Follow-up phone calls to breastfeeding mothers after birth | Sue/Candace/Lynn | 2009-12-01 | 75% | 25% | Tested w/ several clients; Some were doing well and some had given up; Needs continued testing to determine long-term utlity
4 | Play breastfeeding DVD and baby basics DVD on clinic side | Sara/Lynn/Carol | 2009-10-31 | 40% | 60% | Baby Basics DVD currently playing; Researching breastfeeding & infant feeding DVDs; Looking at multi-DVD players
5 | Meet w/ Kathy | Sara/WIC staff | 2009-10-31 | 5% | 95% | Met w/ Kathy; Identified need for staff trainings related to breastfeeding support & promotion of the new WIC food packages; In-staff training in Oct.
6 | Create & purchase incentive bags for Breast is Best participants | Sara | 2009-09-30 | 20% | 80% | Items identified, purchased, and being given out; Still need to be marketed in WIC & clinic; Now ordering bibs or blankets to add
7 | Create a breastfeeding moms bulletin board | Candace/Sara | 2009-10-31 | 75% | 25% | Picture frame magnets designed & being ordered; Must market frames as a reward for breastfeeding; Need to discuss purchasing of digital camera
8 | Display posters of the new WIC food packages in the WIC and clinic lobbies | Sara/Sarah | 2009-09-30 | 10% | 90% | Food purchased, photos taken, and posters printed & displayed!; Awaiting printing of clinic posters and tear pads
2009-09-03
No. | Action/Suggestion/ Recommendation | Person Responsible | Date/Time Due | % Not Complete | % Complete | Resolution/Status
9 | Send out reminder cards to Breast is Best participants the week before they are scheduled | Candace/Sarah | On-going | 0% | 100% | Reminder Cards created & now going out for every scheduled client; Keeping on-going record of show rates & date cards were sent
10 | Meet with hospital lactation specialist | Sara | 2009-07-22 | 5% | 95% | Met with Sandy Rogerson about hospital practices; Awaiting Sandy's decision on us printing business cards for her
11 | Create more inviting atmosphere in Breastfeeding Room | Sara/Lynn/Sarah | 2009-09-10 | 10% | 90% | Rockers arrived & assembled; Artwork nearly complete; Room will be ready for Breast is Best on 9/9/09
12 | Have additional staff trained for breastfeeding support | Becky G., Christine, Eileen, Sarah | 2009-12-05 | 75% | 25% | Becky G., Christine, & Eileen signed up to attend Breastfeeding 101 training; Sarah signed up to attend Lactation Educator Training
13 | Offer Breast is Best class during MCC visit & schedule with WIC | Becky | On-going | 50% | 50% | Becky is already doing this; Need to develop a way for Becky to track if her referrals sign up and attend Breast is Best
14 | Create newsletter for all BCHD staff updating them on the progress of the project | Sarah | 2009-09-30 | 50% | 50% | Text complete; Awaiting feedback & then need to format in Publisher; Need to get incentive bags set up & breastfeeding room complete for pics
15 |  |  |  | 100% | 0%